## Sheet1
Category	Checklist	Comments
NFR	Do we have clarity on scope of work for PT ?		24 January 2024
	Is PT types clearly mentioned including number of cycles/runs for each test type
	Is mapping of NFR with type of testing completed ?
	Is in scope activities clearly documented ?
	Is out of scope activities clearly documented ?
	is tools for different performance test types identified ?
	is Critical Business flows identified ?. Do we have agreement on that functionalities to be performnce tested ? Does it cover 80~90% of core business ?
	is KT for application and flows completed ? Is KT documents like application overview, System appreciation document, logical architecture, physical architecture available ?
	Are the NFRs clearly documented and made available ?
	NFR gathering : who will gather NFR ?
	is NFR availability timeline agreed ?
Environment	Do we have details of team who is responsile for providing the test environment ?.
	Are the roles and responsibilities clearly defined ?
	is duration of PT environment to be made available clearly called out ?
	Are we planning to use shared environment for PT activities ?
	Environment shoul be PROD like, isolated and not shared
	is risk of using environment with lower config/ fewer instances highlighted and mitigated ?
	Have we called the risks of env with scaled down version of PROD env and critical SLA like throughput, Response time cannot be extrapolated ?

Test Data	is data preparation part of PT team ?
	Does PT team have access to database and all servers ? If access is not available, then there will be delay in monitoring and analysis
	Is PROD data redacted in PT environment ?
	is PT team aware of compliance risk of using real data ? ( e.g valid mobile#, email id, credit card )
Interfaces/Stub	If system has interface with other applications, is PT confined to component testing of system under test and PT for interfaces and other upstream/downstream systems are not in scope
	Is PT for interfacing system benchmarked ? If not, there is additional complexity to identify the root cause for performance issue
	If interfacing system is not available or not same size as PROD, then stub needs to be provided by application team